PUBLIC UTILITIES COMMISSION OF THE STATE OF CALIFORNIA

**RESOLUTION TED-313**

Rail Safety Division

**RESOLUTION**

GRANTING EXTENSION OF TIME REQUIRED TO CONSTRUCT EIGHT NEW HIGHWAY-LIGHT RAIL GRADE SEPARATED CROSSINGS AND TWO PEDESTRIAN-LIGHT RAIL AT-GRADE CROSSINGS IN THE CITY OF SAN JOSE, COUNTY OF SANTA CLARA.

By a letter dated February 27, 2025, the Santa Clara Valley Transportation Authority (VTA) requested an extension of time from March 26, 2025, to March 31, 2028, to comply with the provisions of the California Public Utilities Commission (Commission/CPUC) Decision (D.)20-03-022.

D.20-03-022, effective March 26, 2020, authorized VTA to construct eight grade-separated highway-light rail crossings and two at-grade pedestrian-light rail crossings as identified in the table below:

|  |  |  |
| --- | --- | --- |
| **Crossing Name** | **City** | **CPUC Number** |
| Eastridge Station South Ped | San Jose | 082C-15.37-D |
| Eastridge Station North Ped | San Jose | 082C-15.30-D |
| Tully Rd | San Jose | 082C-15.14-B |
| Swift Ln | San Jose | 082C-15.05-B |
| SB Capitol Expressway | San Jose | 082C-14.94-B |
| Cunningham Av | San Jose | 082C-14.61-B |
| Ocala Av | San Jose | 082C-14.37-B |
| Story Rd | San Jose | 082C-13.57-B |
| Northbound Capitol Express Wy | San Jose | 082C-13.25-B |
| Northbound Capitol Av | San Jose | 082C-13.17-B |

VTA is requesting additional time due to delays from legal challenges, which were eventually resolved. VTA awarded the project contract in March 2024. Additional time is needed to construct the entire project as described in D.20-03-022.

The Rail Safety Division's Rail Crossings and Engineering Branch (RCEB) finds that there has been no substantial change in circumstances since granting the original authority, and the VTA's request has merit. RCEB recommends the issuance of this resolution.

IT IS RESOLVED that the Santa Clara Valley Transportation Authority is granted a two-year extension of time from March 26, 2025, to March 26, 2027, to exercise the authority granted in D.20-03-022. In all other respects, D.20-03-022 shall remain in full force and effect.

This resolution is issued pursuant to Resolution Number ET-1367 and memorandum by the Executive Director dated April 6, 1988, and is effective today, April 3, 2025.

sig

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Roger Clugston

Director, Rail Safety Division

Rachel Peterson

Executive Director

California Public Utilities Commission

[rachel.peterson@cpuc.ca.gov](mailto:rachel.peterson@cpuc.ca.gov)

John Ristow

Director Department of Transportation

City of San Jose

[john.ristow@sanjoseca.gov](mailto:john.ristow@sanjoseca.gov)

Matt Loesch

Public Works Director

City of San Jose

[matt.loesch@sanjoseca.gov](mailto:matt.loesch@sanjoseca.gov)

Susan Lucero

Deputy Director of Safety and Compliance

Santa Clara Valley Transportation Authority

[susan.lucero@vta.org](mailto:susan.lucero@vta.org)

Ven Prasad

Engineering Group Manager

Santa Clara Valley Transportation Authority

[ven.prasad@vta.org](mailto:ven.prasad@vta.org)