ALJ/DUG/avs	DRAFT	Agenda ID # 4798

Ratesetting

8/25/2005  Item 53

Decision PROPOSED DECISION OF ALJ LONG  (Mailed 7/19/2005)

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF CALIFORNIA

| Application of SAN DIEGO GAS & ELECTRIC COMPANY under the Catastrophic Event Memorandum Account (CEMA) for Recovery of costs related to the 2003 Southern California Wildfires. (U 902-M) | Application 04-06-035 (Filed June 28, 2004) |
| --- | --- |

OPINION ON THE REASONABLENESS OF SAN DIEGO GAS
AND ELECTRIC COMPANY’S RESPONSE TO THE 2003 WILDFIRES

(See APPENDIX A for Appearance Lists)

TABLE OF CONTENTS

TITLE										         PAGE

Error! Hyperlink reference not valid.

2.  Background	2

Error! Hyperlink reference not valid.

b.  SDG&E 2003 Wildfire Costs Through May 2004	6

Error! Hyperlink reference not valid.

3.  Procedural History	7

Error! Hyperlink reference not valid.

a.  The Standard for Prudent Managerial Action	11

Error! Hyperlink reference not valid.

6.  Restoration Management	14

Error! Hyperlink reference not valid.

a.  ORA’s Examination	16

Error! Hyperlink reference not valid.

1.  Food Services	19

Error! Hyperlink reference not valid.

2.  Avoided Pole Test and Treat Expenses	23

Error! Hyperlink reference not valid.

3.  Franchise Fees and Uncollectibles	25

Error! Hyperlink reference not valid.

4.  Tree Inventory	26

Error! Hyperlink reference not valid.

a.  Allocation of Support Costs to Expense and Capital	27

Error! Hyperlink reference not valid.

b.  Amortization of the Wildfire Account	31

Error! Hyperlink reference not valid.

9.  Labor Costs and Incentive Compensation	31

Error! Hyperlink reference not valid.

10.  SDG&E’s Wildfires Update	34

Error! Hyperlink reference not valid.

12.  Assignment of Proceeding	39

Error! Hyperlink reference not valid.

Conclusions of Law	44

Error! Hyperlink reference not valid.

APPENIDX A

# Summary

This decision finds San Diego Gas & Electric Company (SDG&E) prudently managed its response and allows the recovery of certain recorded costs incurred to restore service and repair or replace those portions of its gas or electric distribution systems damaged or destroyed by a series of catastrophic wildfires.  This decision requires SDG&E to capitalize rather than expense certain support costs ($7.376 million) and allows for an 15-month amortization of the remaining costs charged to expense.  Three reductions are made to the total of recoverable costs:  to adjust for certain avoided future costs for pole inspection and treatment ($42,348), to adjust for excessive costs charged to SDG&E for food service ($582,300), and disallow unjustified incentive compensation accruals ($426,000).  This decision allows SDG&E to recover $39.752 million.

# Background

On June 28, 2004, SDG&E filed an application to recover $37.6 million, the California jurisdictional costs associated with the 2003 Southern California Wildfires (Wildfires).  Applicant asserts the memorandum account (Wildfire Account) is in conformance with its Catastrophic Event Memorandum Account (CEMA) tariff as authorized in its Preliminary Statement.  Including updates through December 2004, SDG&E spent $71.163 million in total, allocated $8.441 million to transmission service subject to the Federal Energy Regulatory Commission’s (FERC) jurisdiction and the balance of $62.722 million to California - jurisdictional gas and electric service.  SDG&E reduced this amount by $21.919 million to reflect funds already authorized in rates.  The remaining $40.803 million are the residual incremental costs that are the subject of this proceeding.

## a.  History of the Wildfires

SDG&E described the Wildfires by citing a joint report of the U.S. Forest Service and the California Department of Forestry and Fire Protection, “In October of 2003, Southern California experienced the most devastating wildland fire disaster in state history.  The facts are staggering – 750,043 acres burned, 3,710 homes lost and 24 people killed including one firefighter.”  The report further states:

“The October Fire Siege of 2003 tested the modern fire service like no other time.  The combined efforts of the largest wildland fire agencies in the world, the United States Forest Service and the California Department of Forestry and Fire Protection (CDF), along with armies of local fire departments across the state mustered ground and air resources into the firefight as never before.  At the peak of the fire siege, over 14,000 firefighters were on the line.  Never in California’s history were so many homes and lives in danger by fire at one moment . . . .  In addition, countless miles of power lines were damaged, communication systems destroyed, watersheds reduced to bare scorched soils, and thousands of people were forced into evacuation centers, unsure if they would have a home to return to – many did not.”

SDG&E further indicates that it believes no area in Southern California may have been harder hit by the wildfires than San Diego County.  It states that approximately 3,200 power poles, 400 miles of wire, 400 transformers and more than 100 other pieces of related equipment were damaged by the fire and needed to be replaced.  Over 2,400 homes were destroyed and countless other structures were damaged by these wildfires.  In addition, SDG&E presents detailed testimony on the scope of the damage to its system attributed to the fire and the response to repair and replace the damage.

In order to invoke and employ the Wildfire Account, SDG&E must demonstrate that the circumstances surrounding the Wildfires meet the conditions for a catastrophic event account as defined in Pub. Util. Code (Code) Section 454.9(a), for restoring utility services to customers, repairing, replacing, or restoring damaged utility facilities, and complying with governmental agency orders in connection with events declared disasters by competent state or federal authorities.  Such costs are recoverable only after the Commission makes a finding of their reasonableness and approves them following an expedited proceeding in response to the utility’s filed application (Code § 454.9(b)).  This proceeding was conducted on a schedule designed to result in a prompt decision after first ensuring due process was provided to all parties.

On October 26, 2003, then-Governor Davis declared a state of emergency in San Diego County.  The following day, October 27, 2003, President Bush also declared a state of emergency in San Diego County.  In addition, the County of San Diego and the City of San Diego also declared states of emergency on October 28, 2003 and November 3, 2003, respectively.  SDG&E invoked its CEMA tariff in response to this catastrophic event, and, in accordance with Resolution No. E-3238, notified the Commission’s Executive Director on November 24, 2003.  The first table below is from Ex. SDG&E-3 and it shows SDG&E’s original cost basis for the request before applying the incremental cost test discussed later in this decision.  The second table is from Ex. SDG&E-4 and it shows the $37.661 million portion of $58.011 million California-jurisdictional costs (through May 2004) that SDG&E claims are reasonable for inclusion in the memo Account and recoverable from ratepayers.  As described in SDG&E’s testimony, $20.35 million was identified to be already available in rates to fund the Wildfire’s costs.  The residual $37.661 million is described as incremental costs, not otherwise provided in rates, and therefore eligible for recovery.  The net request is for $37.309 million for electric costs and $0.352 million for natural gas costs.

The testimony and evidentiary hearings focused on those costs increased through May, 2004.  SDG&E provided two late-filed exhibits (Ex. SDG&E-9 and Ex. SDG&E-10) that updated actual costs through December, 2004.  Those costs are discussed in a separate section of this decision.  Parties reviewed the late-filed exhibits and filed comments that are considered in this decision.

## b.  SDG&E 2003 Wildfire Costs Through May 2004

|  | FERC | CPUC |  |  |
| --- | --- | --- | --- | --- |
| Total | Transmission | Electric | Gas Total |  |
| Costs |  |  |  | CPUC |

| O & M Expenses: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Internal Labor |  | $ 3,787 | $ 212 | $3,320 | $255 | $3,575 |
| Materials |  | 1,348 | 39 | 1,282 | 27 | 1,309 |
| Overhead |  | 2,687 | 149 | 2,360 | 178 | 2,538 |
| Vehicle Charges |  | 445 | 9 | 420 | 16 | 436 |
| External Labor |  | 851 | 133 | 716 | 2 | 718 |
| Services/Other |  | 8,914 | 1,027 | 7,767 | 120 | 7,887 |
| Total O&M |  | $ 18,032 | $ 1,569 | $15,865 | $598 | $16,463 |
| Capital Costs: |  |  |  |  |  |  |
| Internal Labor |  | $ 6,290 | $ 694 | $ 5,565 | $ 31 | $5,596 |
| Materials |  | 3,630 | 861 | 2,766 | 3 | 2,769 |
| Overhead |  | 14,893 | 1,381 | 13,457 | 55 | 13,512 |
| Vehicle Charges |  | 1,817 | 312 | 1,501 | 4 | 1,505 |
| External Labor |  | 18,969 | 3,086 | 15,876 | 7 | 15,883 |
| Services/Others |  | 2,796 | 513 | 2,280 | 3 | 2,283 |
| Total Capital |  | $ 48,395 | $ 6,847 | $ 41,445 | $ 103 | $ 41,548 |
| Total Wildfire |  | $ 66,427 | $ 8,416 | $ 57,310 | $ 701 | $58,011 |

## Proposed Recovery of Wildfire Account Costs Through May 2004

|  | Total CPUC (a) | Memo Account (b) | Current Rates(b) |
| --- | --- | --- | --- |
| O&M Expenses: |  |  |  |
| Internal Labor | $ 3,575 | $ 2,250 | $1,324 |
| Materials | 1,309 | 1,290 | 19 |
| Overhead | 2,538 | 251 | 2,288 |
| Vehicle Charges | 436 | - | 437 |
| External Labor | 718 | 7,546 | 341 |
| Services/Other | 7,887 | 7,546 | 341 |
| Total O&M | $ 16,463 | $12,055 | $ 4,408 |
| Capital Costs: |  |  |  |
| Internal Labor | $ 5,596 | $ 4,060 | $ 1,536 |
| Materials | 2,769 | 2,769 | - |
| Overhead | 13,512 | 636 | 12,876 |
| Vehicle Charges | 1,505 | - | 1,504 |
| External Charges | 1,5883 | 1,5883 | - |
| Services/Other | 2,283 | 2,257 | 27 |
| Total Capital | $ 41,548 | $ 25,605 | $ 15,943 |
| Total Wildfire | $ 58,011 | $ 37,661 | $20,350 |

(a)  Ex. SDG&E-3 Attached Ex. D-1.

- Ex. SDG&E-4, Attached Ex. J.

# Procedural History

Notice of the Application appeared in the Commission’s July 1, 2004 daily calendar.  Resolution ALJ 176-3136, dated July 8, 2004, preliminarily categorized the application as ratesetting and determined that hearings were necessary.  The Commission’s in-house consumer advocacy arm, the Office of Ratepayer Advocates (ORA) filed a timely protest on July 30, 2004.  On July 14, 2004, the ALJ required SDG&E to serve supplemental testimony.  On July 29, 2004, SDG&E served the requested supplemental testimony as Ex. SDG&E-4.  On October 29, 2004, the ALJ required SDG&E to further supplement the testimony contained in Ex. SDG&E-4 and on November 10, 2004, SDG&E served Ex. SDG&E-7 in response.  A Prehearing Conference was held on August 17, 2004 and ORA, the Aglet Consumer Alliance (Aglet) and the Utility Consumer Action Network (UCAN) served timely prehearing Conference Statements.

On August 27, 2003 The Scoping Memo and Ruling of Assigned Commissioner and Administrative Law Judge (Scoping Memo) designated the assigned Administrative Law Judge (ALJ) as the principal hearing officer as defined in Rule 5(l) of the Rules.  It also determined that this is a ratesetting proceeding.  Pursuant to Rule 5(k)(2), the principal hearing officer is the presiding officer for this proceeding, and is responsible for issuing the proposed decision pursuant to Code § 311(d) and Rule 8.1.

The scope of this proceeding was identified as:

- Reasonableness of SDG&E’s overall management of the restoration of service in a safe and timely manner, consistent with worker safety, public need, and equitable treatment of customers.

- Reasonableness of the gross amount of Operating & Maintenance Expenses recorded in the Wildfire Account.

- Reasonableness of the gross amount of Capital Expenditures recorded in the Wildfire Account.

- Reasonableness of SDG&E’s determination of incremental costs as defined by Resolution E-3238.

- Reasonableness of the forecast 2005 ongoing capital-related costs of $4.3 million for electric distribution and gas revenue requirements.  This includes an analysis of any 2005 incremental or avoided expense or capital expenditure impacts on SDG&E’s subsequent operations as a result of service restoration after the Wildfires.

- Allocation of all costs between the jurisdictions of the Federal Energy Regulatory Commission and the California Public Utilities Commission.

- The reasonableness and timing of SDG&E’s proposed ratemaking treatment of any authorized recovery of the Wildfire Account balances.

Testimony was served by ORA and UCAN on October 22, 2004.  Evidentiary hearings were conducted on November 15 – 16, 2004, and over 20 exhibits were received in evidence.  All issues are ready for consideration.

In accordance with the Scoping Memo, opening and reply briefs were filed by SDG&E, ORA, and UCAN, on December 3, 2004 and December 10, 2004, respectively.  A late-filed exhibit, Ex. SDG&E-9, was served to update the balance in the Wildfire Account.  It was received into evidence on January 18, 2004, and on February 7, 2005 ORA and UCAN filed comments.  SDG&E served an errata, Ex. SDG&E-10 on February 4, 2005 and it was received into evidence.  The matter was submitted on February 9, 2005.  This decision adopts rates consistent with Ex. SDG&E-9 and Ex. SDG&E-10 as modified for the reasonableness adjustments to the recorded costs.

# The Burden of Proof

There is a natural litigation advantage enjoyed by utilities, and the fact that we must rely in significant part on their experts, reinforces the importance of placing the burden of proof on the applicant utilities.  SDG&E has the sole obligation to provide a convincing and sufficient showing to meet the burden of proof, and any active participation of other parties can never change that obligation.  This was clearly described in D.87-12-067 as follows:

“The inescapable fact is that the ultimate burden of proof of reasonableness, whether it be in the context of test year estimates, prudence reviews outside a particular test year, or the like, never shifts from the utility seeking to pass it costs of operations onto ratepayers on the basis of the reasonableness of those costs.”  And further:

“The longstanding and proper rule is set forth in D.90642 at 2 CPUC 89, 98-99 and requires that the utility meet its burden by clear and convincing evidence.  To meet this burden we have specified that “… the applicant must produce evidence having the greatest probative force.””

SDG&E and ORA did not discuss the burden of proof in opening briefs.  In its opening brief, UCAN argues that SDG&E bears the burden of proof to “demonstrate the reasonableness of its application, SDG&E must support each component of its proposed request through clear and convincing evidence.”  UCAN correctly states the law, as applied in this decision.  SDG&E must meet its burden of proof and demonstrate that in fact its responses to the 2003 Wildfires were prudent and consistent with the Commission’s standard for prudent managerial action.  Finally, it is the utility, not the staff or interested parties that faces the burden of showing with clear and convincing evidence that its course of action was reasonable and therefore entitled to compensation.  As discussed below we find that in this proceeding SDG&E has met its burden, except where otherwise found.

## a.  The Standard for Prudent Managerial Action

The Commission’s standard in a reasonableness review of managerial action is settled.  In a reasonableness review of the 2003 Wildfires, and consistent with previous statements of the standard, SDG&E should be held to the following standard:

“Utilities are held to a standard of reasonableness based upon the facts that are known or should be known at the time.  While this reasonableness standard can be clarified through the adoption of guidelines, the utilities should be aware that guidelines are only advisory in nature and do not relieve the utility of its burden to show that its actions were reasonable in light of circumstances existent at the time.  Whatever guidelines are in place, the utility always will be required to demonstrate that its actions are reasonable through clear and convincing evidence.”

Thus, the reasonableness of a particular management action depends on what the utility knew or should have known at the time that the managerial decision was made, not how the decision holds up in light of future developments.  The Commission has affirmed this standard of review in numerous decisions over many years.

The term ‘reasonable and prudent’ means that at a particular time any of the practices, methods, and acts engaged in by a utility follows the exercise of reasonable judgment in light of facts known or which should have been known at the time the decision was made.  The act or decision is expected by the utility to accomplish the desired result at the lowest reasonable cost consistent with good utility practices.  Good utility practices are based upon cost effectiveness, reliability, safety, and expedition.

“A ‘reasonable and prudent’ act is not limited to the optimum practice, method, or act to the exclusion of all others, but rather encompasses a spectrum of possible practices, methods, or acts consistent with the utility system needs, the interest of the ratepayers and the requirements of governmental agencies of competent jurisdiction.”

The standard of reasonableness does not derive from the consequences of managerial action, but the soundness of the utility's decision-making process that led to the decision and the consequences:

“Thus, a decision may be found to be reasonable and prudent if the utility shows that its decision making process was sound, that its managers considered a range of possible options in light of information that was or should have been available to them, and that its managers decided on a course of action that fell within the bounds of reasonableness, even if it turns out not to have led to the best possible outcome.  As we have previously stated, the action selected should logically be expected, at the time the decision is made, to accomplish the desired result at the lowest reasonable cost consistent with good utility practices.”

The Commission has noted that this standard can prove difficult to apply:

“The reasonable and prudent act is not limited to the optimum act, but includes a spectrum of possible acts consistent with the utility system need, the interest of the ratepayers, and the requirements of governmental agencies of competent jurisdiction.”

And

“The burden rests heavily upon a utility to prove with clear and convincing evidence, that it is entitled to the requested rate relief and not upon the Commission, its staff, or any interested party to prove the contrary.”

Thus, although the utility need not show that it has undertaken the optimal act, it must show that its course of action was reasonable and that the utility took care in making its decision.

# Review by Other Parties

UCAN proposes in its opening brief a standard of review that would preclude SDG&E from recovery of costs subject to the CEMA tariff provisions unless ORA performed a review sufficient to meet the standards as asserted by UCAN.  This argument would shift the burden of proof to ORA – it would unreasonably shift to ORA the Commission’s obligation to determine whether a utility behaved in a reasonable fashion.  Neither UCAN nor ORA are obliged to review an application by SDG&E before the Commission can make a finding on reasonableness: their appearance often informs the proceeding; but it is not a precondition for the Commission to reach a decision.

UCAN relies on a decision rejecting a settlement where ORA assumed the burden of a settling party to show that the settlement was fair.  Our standard for a settlement is established in Rule 51.1(e) that requires it to be “reasonable in light of the whole record, consistent with law, and in the public interest.”  The Commission found in D.01-02-075 that ORA had not performed sufficient analysis, so as to have an adequate and informed opinion, necessary to settle with SoCalGas.

In this proceeding, ORA has overstated the conclusion to be drawn from its analysis; it is clear it did not do sufficient analysis beyond determining whether SDG&E’s costs were incremental to existing rates:  therefore we find that ORA has no well-founded objections to SDG&E’s request.

UCAN’s interpretation of D.01-02-075 would tie the hands of the Commission giving ORA a virtual veto over any rate recovery.  If ORA did not participate, logically according to UCAN, we could not find the applicant’s request to be reasonable.  As noted previously, this is not the case.

# Restoration Management

This section addresses the reasonableness of the overall management response to the Wildfires.

SDG&E presented testimony describing its response to the Wildfires, beginning with monitoring and rapidly progressing to activation of an “emergency desk” and finally the activation of SDG&E’s Emergency Operations Center.  Ultimately SDG&E decided to call for assistance on other utilities, Arizona Public Service Company, Pacific Gas and Electric Company, Sacramento Municipal Utility District, Sierra Pacific Power Company, Tucson Electric Power, the Salt River Project, and the Western Area Power Authority.  All of them were reimbursed by SDG&E and the costs are included in the Wildfire Account.  Southern California Edison Company was at risk from the fires and was not called on for assistance.  The use of mutual assistance crews and additional contractor personnel was necessary to restore service in a timely fashion.

Senior management was involved in the oversight of the project and SDG&E systematically (to the extent possible following the fires) tried to reestablish service as quickly as possible.  As a result, the company had to quickly assess the damage and plan a coordinated response.  We find that SDG&E has met its burden of proof to show that it actively engaged in a reasonable response directed and supervised by senior management in a coordinated manner.  SDG&E used a central management process that gave it the best opportunity to respond to the Wildfires in a rational and responsible fashion with the information that was available during the project.  The use of the Emergency Response Center, and the operational decisions described in the testimony and in this record, meet the prudent manager standard.

# Reasonableness of Costs

This section addresses SDG&E’s prudence in controlling and reasonably managing the costs incurred to restore service following the 2003 Wildfires.  Before we can consider the reasonableness of the proposed allocation of costs to retail customers we must first examine the total costs incurred, consider any available revenues to offset to these costs to determine the incremental costs, and then determine the appropriate allocation of incremental costs.

SDG&E stated that it had no insurance coverage that would reimburse the costs of the Wildfires.  The justification is the cost of insurance estimated at $10 million annually with limits of $20 million in coverage.  Thus in about six-years the premiums would have equaled the cost of the Wildfires and coverage would have only reimbursed a third of the costs.  Based on this explanation it is reasonable not to expect insurance coverage for these costs.

SDG&E used an “incremental cost criteria” to calculate costs includable in the Wildfire Account.  That is, the company assumed direct labor at straight - time (excluding overtime) and other costs that were incurred solely to restore service are incremental to existing costs already included in rates.  SDG&E stated its belief that this approach is in conformance with Resolution E-3238.  ORA concludes that SDG&E’s calculations of incremental costs are a reasonable basis for recovering the Wildfire Account.  ORA further supports the recovery of the incremental costs either through the amortization of the expenses included in the Wildfire Account and the capital expenditures added to SDG&E’s rate base, as calculated by SDG&E.  UCAN notes various adjustments and proposes several specific disallowances, and in addition to those issues which are discussed below, UCAN otherwise opposes the rate recovery of the Wildfire Account costs based on its burden of proof arguments.

We find that, except for the changes adopted in this decision, SDG&E has otherwise accounted for its costs in a reasonable manner and it is reasonable to allow rate recovery of the Wildfire Account costs (after adjustment).

## a.  ORA’s Examination

ORA’s prepared testimony in Ex. ORA-1 indicates that its staff conducted a review of the costs incurred to restore service and found only the one exception noted in its testimony.  Otherwise, ORA believes the incremental costs to be reasonable.  Under cross examination by UCAN, ORA was asked about its finding that SDG&E has only included costs in the Wildfire Account that are incremental to existing allowances in rates, are related solely to the restoration of service after the Wildfires, and are recoverable within the definition of the catastrophic event memorandum account.  UCAN questioned ORA’s witness on the criterion used in its testimony to determine, for example, that “ORA finds the remaining Services/Other costs to be reasonable and SDG&E should be allowed to recover these costs in rates.”

ORA did not evaluate the costs included in the account against an objective standard in order to form an opinion on whether or not SDG&E had paid an excessive price.  ORA’s analysis was limited to determining whether, in its opinion, the costs were incremental to allowances existing in rates and the costs were only incurred to restore service after the Wildfires.

The one cost recovery exception noted by ORA is to exclude from recovery $9,146 for advertisements used to publicly thank the other utilities that provided mutual assistance to SDG&E.  We will adopt this minor adjustment, with which SDG&E has agreed, not because the utilities were reimbursed for their costs, as suggested by ORA, but because it is an unnecessary cost to restore service.

ORA again limited its review in this proceeding to the same level where it was criticized in D.01-02-075 because it “did not review the reasonableness of the expenditures from a cost causation perspective or from a cost reduction or avoidance perspective.”  In future reviews of catastrophic event memo accounts we believe that ORA should not limit its analysis to whether or not the costs were incremental.  We believe that ORA should also “review the reasonableness of expenditures for a cost causation perspective or from a cost reduction or avoidance perspective” as we have previously stated in D.01-02-075.

## b.  UCAN’s Recommendations

UCAN submitted prepared testimony in Ex. UCAN-151, which makes several recommendations:

1.  Disallow $738,400 for food-related costs that cannot be justified. (p. 6.)

2.  An estimated $42,348 in pole test and treat expenses avoided over the next 4 years should be offset against the Wildfire Account O&M expense.  (p. 7.)

3.  Prior to evidentiary hearings, UCAN was concerned that SDG&E used an incorrect franchise fee and uncollectible allowance for an error of $67,000.  (p. 10.)

4.  UCAN expresses a non-monetary concern that SDG&E’s tree-trimming inventory has increased, rather than decreased in the fire-damaged area.  (p. 8.)

5.  SDG&E incorrectly accounts for $7.2 million in various Support Services as an expense, which should be allocated between expense and capital (rate base) based on the relative split of direct labor - 15.8% to expense and 84.2% to capital.  (p. 9.)

6.  Because of the rate impact of SDG&E’s Cost of Service A.02-12-028 (2004 increase under collection plus 2005 attrition increase.) the Commission should amortize the Wildfire Account over 2 years instead of 1.  (pp. 10-11.)

UCAN applies an additional reasonableness test to SDG&E’s request that was not employed by ORA.  UCAN argues that some of SDG&E’s costs are excessive when compared to a fair market price for the commodity.  UCAN does not dispute that SDG&E incurred the costs nor does it disagree with SDG&E’s process for allocating costs to the Wildfire Account.  It does take exception to the ratemaking treatment of certain costs.  UCAN in total considered cost causation, cost reduction and cost avoidance as a part of its examination of SDG&E’s proposals.

### Food Services

The company spent $5.4 million to provide meals, snacks, water and other items, and over 92,000 meals.  UCAN could not determine the accuracy of the 92,000 meal count.  UCAN disputes the total based upon the duration of the project and the number of personnel involved.  UCAN first equates the total to 30,677 person-days of meals, assuming 3 meals per day.  Next, UCAN argues that the personnel counts provided by SDG&E in testimony and data responses total only 1,339 and not 1,800 as stated by the company in Ex. SDG&E-2 and this suggests 5,400 meals a day not the 6000 included in Ex. SDG&E-2.  UCAN expresses a concern with SDG&E’s contract management practices and concludes that SDG&E did not exercise sufficient reasonable control over costs or the performance of some vendors.

| UCAN’s Food Service Analysis |  |  |
| --- | --- | --- |
| Meals | 27% | $1,458,000 |
| Snacks | 9% | 486,000 |
| Drinks (water, Gatorade, etc.) | 28% | 1,512,000 |
| Staff & Set Up | 15% | 810,000 |
| Other Ancillary (tents, porta-potties) | 15% | 810,000 |
| Tax | 7% | 378,000 |
| Total (rounded) | 100% | $5,454,000 |

UCAN closely examined the snack and drink (snacks) cost of approximately $2 million and took exception to the costs incurred for Gatorade, bottled water and Red Bull energy drink.  UCAN opined that SDG&E paid its vendors a significant premium compared to the nearby COSTCO in La Mesa, California, and based on a daily consumption calculation, determined that SDG&E was over-charged by $582,300.  UCAN pointed out that not only did employees appear to consume extraordinary quantities (even after allowing for the prevailing conditions) but that SDG&E exercised no reasonable control over unit costs.  UCAN justifies the disallowance by showing that the other costs included in a typical retail price are already separately charged to the Wildfire Account as ancillary costs and labor.

SDG&E’s rebuttal testimony objects to UCAN’s price comparison and argues that it “did not have the luxury of time or resources to evaluate all options ahead of time, plan out exactly what was needed and then competitively bid for these emergency services and supplies.”  SDG&E argues too that it was against company practices for employees to make purchases on behalf of SDG&E without going through established processes”  SDG&E also argues that UCAN made a simplistic count of meals without considering such things as some tired and hungry employees (Ex. SDG&E-4) ate more than a single portion, there was no “rationing,” the incidental feeding of police, fireman and even fire victims, and overall, UCAN did not consider the complexity of the project to quickly restore service after the wildfires.  The company concludes that it “followed its procedures and generally accepted practices and utilized established catering firms that it believed could meet the challenge during this extraordinary time.  The unit prices for meals, snacks and drinks were in line with typical rates utilized by the catering industry.”

UCAN proposes to apply a further appropriate test to the costs that is more rigorous than the ORA tests discussed above.  UCAN argues that SDG&E unreasonably paid excessive prices that were charged by the food service vendors for the basic commodities of bottled water and various energy drinks by failing to exercise reasonable control over the contractors or its own employees.

#### Discussion

The essential question is whether SDG&E exercised sufficient control over its vendors to ensure that despite the desperate situation of the Wildfires it paid reasonable prices for essentially basic commodities:  bottled water, energy drinks, and snacks.  UCAN argues convincingly that all overhead for the vendors, labor, tents, etc., were fully recovered separately and therefore the implicit conclusion is that the mark-ups on the commodities paid by SDG&E are unreasonable.  To disallow the snack costs identified by UCAN it is necessary to find whether SDG&E would have failed the prudent manager standard discussed above.

SDG&E cannot avoid its responsibility to prudently control all costs by merely pointing to a contract with its vendors.  Taking the time to properly manage contracts and control costs is not a luxury; it is SDG&E’s obligation in exchange for recovering its reasonable costs.  SDG&E offers no evidence that it actively controlled costs, except for a blanket 10% reduction negotiated after the fact with one vendor.  We agree with UCAN that regardless of the circumstances, the company has an obligation to ensure that the price it pays for standard food service products is reasonable.  The COSTCO prices are an adequate proxy for a fair market price; these may not be the lowest possible price considering the huge volumes involved, but they are a clearly available local option.  SDG&E tries to suggest that the COSTCO comparison is trivial, but the issue is important.  We do not suggest that workers did not need these foodstuffs in reasonable quantities, but that SDG&E failed to exercise adequate control and wasted over half a million dollars by not managing the costs of support service contracts.  The other costs incurred by the vendors were fully compensated by SDG&E, and we have no reason to find that these drinks were the sole source of profit margin to the vendor.  Therefore we will disallow $582,300 for SDG&E’s failure to ensure that the snack food prices for standard food service products were charged at a reasonable market price.

UCAN argues in its opening brief that food services costs should be further reduced by $113,111 based on its calculation of extra (i.e., unnecessary) meals.  UCAN argues that the contract should have been on a per person basis, not a meals-equivalent.  The contracts with Ranch Catering, for example, did not impose a head count condition on payment; nor can we determine whether the unit cost would have changed if the obligation was to feed everyone on a per-person charge.  SDG&E argued it wanted no worker to go back to work hungry and so it did not ration food.  We accept that the workers quite likely ate more than a single standard serving of food as measured by the caterers, and we accept as reasonable that SDG&E did not want the workers to lack sufficient volume of appropriate food and beverages.

The Wildfires were a unique event (otherwise CEMA would not apply) and thus the prudent manager standard has to be applied with consideration of the unique circumstances of the Wildfires.  SDG&E does not regularly feed its field construction and repair personnel and so we expect reasonable care over catering contracts but we cannot expect perfection.  We will not make the additional disallowance to meals.

### Avoided Pole Test and Treat Expenses

UCAN determined that SDG&E replaced 2,872 poles used for distribution service, and that 73% of the destroyed poles (2,096) were over 15 years old which put them on a 10-year inspection and treatment cycle.  UCAN believes that no inspection will be needed on the new poles during the next 10 years and this will avoid inspections at $34.29 per pole.  UCAN allows for the 30% of 2,096 older poles (861) that were already inspected before they were destroyed by the fire so SDG&E only avoids inspecting the remaining 70% or 1,235 poles that were destroyed before inspection.  Savings calculated by UCAN total $42,348.  UCAN proposes to offset this amount from the Wildfire Account and avoid the complication of adjusting base rates to reduce the number of pole inspections forecast in base margin rates.

SDG&E responds that an offset is unreasonable because under conventional cost of service ratemaking “practices do not require the utility to expend every dollar of its authorized revenue requirement as the utility may have predicted would be necessary in its cost of service application.  To the contrary, traditional test year ratemaking principles permit the utility to redeploy its authorized revenue requirement in order to accommodate the real world circumstances it encounters during the test period.”  SDG&E argues further that money “saved from avoiding inspections of the recently replaced poles, if not needed for inspection and treatment of other poles, will most likely be spent on other reliability-related activities.”

#### Discussion

We are not persuaded by SDG&E’s ratemaking argument, because the CEMA process itself is an exemption to accommodate the real world during the test period so that SDG&E does not have to bear the entire cost of a disaster like the Wildfires.  It appears that SDG&E wants to pass along the

unanticipated costs of the Wildfires without surrendering the savings if other costs are avoided.  The company accuses UCAN of “cherry-picking” an issue where costs are likely to be avoided while ignoring “those that could cause future costs to increase,” without citing any probable cost increases.  UCAN’s suggestion is not extreme or improbable; it is a reasonable recognition that a large number of unexpected new poles displaced older poles that would otherwise have to be inspected in the near-term.  Additionally, this savings is from revenues otherwise already in rates that will not need to be spent and is available to offset a very small part of the Wildfire Account.  Our guidelines in Resolution E- 3238 anticipate this type of offset by looking for available revenues already in rates.  We will require SDG&E to offset the $42,348 savings for pole inspection and testing against the Wildfire Account balance.

### Franchise Fees and Uncollectibles

SDG&E requests $627,000 for both franchise fees and otherwise uncollectible revenue (billed to customers but never collected).  Initially UCAN identified what it believed to be a computational error of $7,000 for Franchise Fees and Uncollectibles.  SDG&E testified that the correct calculation is to increase the recoverable costs ($15,300,000) by a factor that recovers both the uncollectible allowance and the appropriate franchise fees.  This is a typical ratemaking convention to ensure the utility an opportunity to recover the full amount of authorized revenues.  The calculation has to allow for a full recovery including collecting from all customers the amount otherwise uncollectible from a few, plus the franchise fees SDG&E must pay on the total.  SDG&E calculates the gross-up factor as: 1 / 1 – (3.67% + 0.266%) = 1.041.  The revenue requirement request after “grossed-up” is $15,300,000 x 1.041 = $15,927,000.

#### Discussion

UCAN withdrew its testimony without further explanation following SDG&E’s rebuttal.  After reviewing SDG&E’s calculation we agree that it has made the correct calculation for recovery of the franchise fee and otherwise uncollectible revenues.  We will use this method as a part of the calculation of the final revenue requirement authorized in this decision.

### Tree Inventory

UCAN argues that SDG&E has been removing large numbers of trees as a result not only of the Wildfires but also due to the bark beetle infestation that killed many trees and led to a programmatic removal of affected trees.  UCAN points out that a tree inventory before October 6, 2003, i.e., prior to the Wildfires, showed 145,575 trees.  A September 2004 inventory showed 145,661 trees, an increase of 86 trees.  UCAN is concerned that after the removal of numerous trees due to the Wildfires and the bark beetle, the inventory tally should have clearly fallen, and that SDG&E needs to explain this anomaly.

SDG&E explains in rebuttal that many scorched trees are retained in the inventory until they determine whether or not the tree will survive.  Additionally, SDG&E added scorched trees outside the rights-of-way and not in the previous inventory because they may fail and could subsequently fall into the overhead lines.

SDG&E’s explanation is reasonable and no further action is necessary at this time.

# Ratemaking Treatment

This section addresses the reasonableness of the ratemaking proposal to recover the reasonable costs of the 2003 Wildfires.  Included in this section are two of UCAN’s proposals.

## a.  Allocation of Support Costs
to Expense and Capital

UCAN argues that SDG&E inappropriately categorized various support costs totaling about $7.2 million as expense rather than allocating the costs between expense and capital expenditures includable in rate base.  UCAN uses an allocation factor of labor costs and calculates that 15.8% should be expensed and 84.2% should be capitalized.  According to UCAN, SDG&E used the too literal assumption that meals and lodging are consumed and should be expensed.  UCAN objects to SDG&E’s accounting interpretation that environmental support costs ($1.2 million of the total) were not incurred as a part of new construction.  UCAN also argues that some environmental costs were clearly for pole replacement and reconductoring projects, but for simplicity it did not compute a separate environmental allocation.  UCAN proposes to allocate these costs in proportion to direct labor.  The effect of UCAN’s recommendations is to allocate a larger share of the support costs to capital which results in rate recovery through depreciation over a longer period of time.

SDG&E’s proposal to expense these overheads is based on its interpretation of the applicable accounting standards that these costs were “consumed” concurrently and should not be capitalized as a part of the costs of installing new long-lived assets.  SDG&E’s witness testified, however, that this was an interpretation and could not cite a specific pronouncement or interpretation in any of the prepared testimony’s general references to generally accepted accounting principles (GAAP), the Code of Federal Regulations (explained to be intended as the applicable uniform system of accounts) or SDG&E’s own internal accounting practices.

### Discussion

Our well-established ratemaking practice is consistent with the matching principle or concept in accounting.  That principle requires costs incurred for current service to be “expensed” in a single year and all of those costs that are necessary to provide service over many years to be “capitalized” and recovered over the useful life of the underlying asset.  In this proceeding, many physical assets, poles, wire, transformers, etc., that were destroyed by the Wildfires were capitalized when they were originally placed in service.  The full cost of replacing those assets should likewise be capitalized.

Looking first to the overhead costs including meals and snacks, etc., we believe that SDG&E has applied a very literal interpretation of current consumption and chooses to focus on the fact that employees ate or drank (currently consumed) the commodity rather than examine why the cost was incurred.  SDG&E could have restored service more slowly at a much lower cost without mutual aid crews from other utilities, without additional contractor employees, without incurring double-time and without the provision of food and shelter to these workers.  But, in order to restore service at extraordinary speed, it incurred all of these costs, restoring service to great praise for itself and to the overall benefit of all customers.  The only way to have reduced the capital costs would have been to incur lower costs by working more slowly (avoiding double-time, meals, etc.).

As discussed under the management of the project, we found SDG&E to be reasonable in its many decisions, big and small, on how to reasonably restore service.  That finding does not automatically extend to the ratemaking consequences.  Under SDG&E’s interpretation of consumption, more costs are recovered quickly by including them in the current amortization portion of the Wildfire Account (i.e., “expensing” the costs).  But that interpretation misrepresents the full capital costs incurred.  SDG&E’s decision to expedite service restoration resulted in the utility paying overtime, providing meals on site, and providing accommodation to extra workers, all of which directly increased the cost to install new plant.  We accept that SDG&E’s decision to expedite was reasonable and it was in the public interest to restore service quickly.  Such a decision by SDG&E led directly to incurring higher and additional costs compared to the cost of restoring service more slowly and at great hardship to ratepayers.  While agreeing that these costs should be recorded, UCAN contends that this approach resulted in higher construction costs for long-lived assets which UCAN believes should be capitalized and recovered over the useful lives of the assets just like the direct costs of the poles, wires, transformers and the normal labor costs.  UCAN argues that the split should be 15.8% of support costs to expense and 84.2% to capital.  UCAN argues the costs should follow the allocation of internal and external labor.

We do not agree with SDG&E’s interpretation to expense all support costs, including meals and accommodations, and we direct SDG&E to capitalize its support cost overheads in proportion to the split of direct costs between expense and capital.  This decision does not preclude SDG&E from recovering all of its reasonable costs, but it does allocate a larger portion to capital.

With respect to the environmental costs, UCAN argues that SDG&E failed to allocate appropriate environmental support costs to capital projects.   The record clearly shows that SDG&E recorded $1.320 million in environmental costs to operating and maintenance expense and only $0.003 million to capital.  SDG&E only capitalized $3,000 for environmental costs out of the total $25,605,000 that is capitalized by SDG&E.  UCAN suggests using the labor cost allocation as a proxy to allocate the environmental costs.  We agree that SDG&E’s allocation of all support costs, including environmental costs, almost exclusively to operating and maintenance expense is arbitrary and does not reflect a reasonable allocation of costs between expense and capital.  SDG&E does not offer a detailed analysis that would support the conclusion that environmental costs were overwhelmingly expense-related and not capital related.  We will direct SDG&E to allocate environmental costs between expense and capital in proportion to the direct costs, i.e., 15.8% of support costs to expense and 84.2% to capital.

## b.  Amortization of the Wildfire Account

SDG&E requests a 12-month amortization for the expense portion of the Wildfire Account beginning January 1, 2005.  UCAN proposes that the amortization should be doubled to 2 years, citing the impact of rate changes likely in A.02-12-028 for a test year 2004 as well as any attrition allowance for 2005.  There are other likely rate impacts too.

### Discussion

In fact this decision will not be implemented in time to begin amortization on January 1, 2005.  A reasonable compromise is readily available to us to begin amortization on October 1, 2005 for 15 months through December 2006.  This will conveniently allow amortization to begin shortly after this decision is adopted and its end will coincide with the next base margin adjustment likely to occur on January 1, 2007.

# Labor Costs and Incentive Compensation

SDG&E incurred labor costs of $10.076 million to restore services after the Wildfires.  ORA performed test procedures and in its opinion verified that this expenditure is supported by payroll records and was credibly incurred.  ORA’s testimony notes no exceptions to SDG&E’s labor costs.

SDG&E made the assumption that all “straight-time” cost of employee labor was not an incremental cost:  it was essentially already included in rates, available to restore service, and therefore was not includable in the Wildfire Account.  We agree with SDG&E that this is a reasonable convention for catastrophic event cost recovery.  SDG&E identifies $726,000 of “time-and-a-half” and $5,581,000 of “double-time” labor costs as both incremental and allocable to California-jurisdictional gas and electric service, because these costs were incurred solely due to the Wildfires.  We find that SDG&E has justified its request to recover these direct labor costs in the Wildfire Account.

In addition to the direct costs of $10.076 million for labor, SDG&E also recorded $726,000 for incentive compensation, and allocated $426,000 as incremental costs to be recovered in the Wildfire Account.

| Labor | Cost | Incentive | Percent |
| --- | --- | --- | --- |
| Union | $8,209,536 | $380,838 | 4.64% |
| Non-Union & Non-Management | 269,579 | 44,724 | 16.59% |
| Cash Awards & Other | 15,000 | 0 | - |
| Management | 1,583,304 | 300,881 | 19.00% |
| Total | $10,077,422 | $726,443 |  |

## Discussion

The record shows that SDG&E did not adjust incentive compensation charged to the Wildfire Account to reflect any actual payment of incentives awarded were specifically attributed to employee performance during the wildfires project.  ORA made no examination of the process by which employees might have been awarded incentive compensation for their performance.  SDG&E’s witness confirms that there was no attempt to verify the award of incentives, and that the application assumed an automatic accrual.

In A.02-12-028, SDG&E’s most recent base margin proceeding, expert testimony was presented by the President and the Vice President of Human Resources, who both testified that SDG&E’s incentive compensation program was not an automatic entitlement; that employees were awarded incentive compensation based upon their performance in relationship to specific goals and objectives.

“Well, variable compensation generally has to be re-earned from year to year by individuals.  So having specific goals either individual or company goals on a year-to-year basis would require that person to meet those individual goals and the company meet the corporate goals.”  (Rowland, Transcript p. 1422, A.02-12-028.)  And elsewhere:

“The performance review process is an element of how you get to the calculation of incentive compensation.”  (Giles, Transcript p. 255, A.02-12-028.)

The testimony in A. 02-12-028 showed that although employees might expect some incentive compensation, it was not automatic.  In this application, SDG&E’s witness testified that the incentive compensation recorded in the Wildfire Account was a mechanical accrual and was not reconciled to any actual incentives that might have been awarded to employees specifically for their performance during the Wildfires service restoration project.  In fact the testimony contradicts the policy statements in A.02-12-028:

“The (incentive compensation) is paid to employees as part of their compensation.  It’s based on their eligible wages, and to the extent that they had increased wages because of the fire storm, then there was an ICP payout relative to those wages.” (Shepherd, Transcript p. 102.)

SDG&E’s witness testified in this proceeding that the company “applied that rate at target against the incremental labor” and thus did not take into consideration whether employees would actually receive incentive compensation in conformance with the compensation plan policies.  The witness assumed “payout” would occur in the subsequent year (which would be 2004) and did not reconcile the request to actual awards, if any.

Clearly employees worked hard and for long hours to restore service; indeed, $6.5 million was spent on double-time labor and $5.6 million is included in the Wildfire Account.  What is not supported by SDG&E is why management employees are entitled to a 19% bonus or indeed why any bonus should be automatically accrued on top of double-time pay for non-management employer.

SDG&E has not shown clear and convincing evidence that the incentive compensation recorded in the balancing accounts was in fact earned and awarded to employees specifically as a result of the company’s incentive compensation program for actions attributed to work performed immediately after the Wildfires to restore service.  Nor is it reasonable to treat an incentive mechanism as automatic.  Therefore we disallow $426,000 of incentive compensation from the Wildfire Account.

# SDG&E’s Wildfires Update

When SDG&E filed A.04-06-035, $66.4 million had already been recorded to SDG&E’s Wildfires Account through May 31, 2004.  As updated in Ex. SDG&E-9, SDG&E’s actual total firestorm costs recorded through December 31, 2004 are $70.6 million, representing a difference of $4.2 million from May 31, 2004.  According to SDG&E, the difference is the result of approximately $0.2 million of O&M (primarily environmental costs and accounting adjustments) and $4.0 million of capital expenditures primarily incurred for the rebuilding of Circuit 79 and the smaller amount spent on Circuit 176 that serves the eastern area of the city of Poway.

Additional cost of $2.9 million recorded through December 31, 2004 are incremental Commission jurisdictional costs, and according to SDG&E, the balance of $1.3 million is non-incremental and should be excluded from the Wildfires Account.  The capital costs were not included when the application was filed because SDG&E records the costs in the Wildfires Account after the work is completed.

On February 4, 2005, SDG&E filed Ex. SDG&E-10, which as errata to Ex. SDG&E-9, made several adjustments to the update.  As updated in Ex. SDG&E-10, SDG&E’s actual total firestorm costs recorded through December 31, 2004 are $71.1 million, representing an increase of $4.7 million ($71.1 million less $66.4 million) from May 31, 2004.  Thus the errata, Ex. SDG&E-10, increased the total by $500,000 compared to the Late-filed Update Ex. SDG&E-9 ($71.1 million less $70.6 million).

Wildfire Costs Including Update & Errata

|  | FERC |  | CPUC |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Total Cost | Electric Transmission | Electric Distribution | Gas | Total CPUC |
| O&M Expenses: |  |  |  |  |  |
| Pre-Update O&M | $ 18,032 | $ 1,569 | $ 15,865 | $ 598 | $ 16,463 |
| Internal Labor | $ 11 | 1 | $ 10 | $ - | $ 10 |
| Materials | 4 | (1) | 5 | - | 5 |
| Overhead | 10 | 1 | 9 | - | 9 |
| Vehicle Charges | (2) | - | (2) | - | (2) |
| External Labor | 8 | - | 8 | - | 8 |
| Services/Other | 225 | 16 | $ 208 | 1 | 209 |
| Update & Errata | $ 256 | $ 17 | $ 238 | 1 | 239 |
| Total O&M | $ 18,288 | $ 1,586 | $ 16,103 | $ 599 | $ 16,702 |
| Capital Costs: |  |  |  |  |  |
| Pre-Update Capital | $ 48,395 | $ 6,847 | $ 41,445 | $ 103 | $ 41,548 |
| Internal Labor | $ 47 | - | $ 41 | $6 | 47 |
| Materials | 19 | - | 17 | 2 | 19 |
| Overhead | 1,229 | 2 | 1,213 | 14 | 1,227 |
| Vehicle Charges | 30 | - | 29 | 1 | 30 |
| External Labor | 342 | - | 342 | - | 342 |
| Services/Other | 2,813 | 6 | 2,807 | - | 2,807 |
| Update & Errata | 4,480 | 8 | 4,449 | 23 | 4,472 |
| Total Capital | $52,875 | $ 6,855 | $ 45,894 | $ 126 | $46,020 |
| Updated Total | $ 71,163 | $ 8,441 | $ 61,997 | $ 725 | $ 62,722 |

According to SDG&E, the final difference is the result of approximately $0.3 million of O&M (primarily environmental costs and accounting adjustments) and $4.4 million of capital expenditures primarily incurred for the rebuilding of Circuit 79 and the smaller amount spent on Circuit 176 that serves the eastern area of the city of Poway.  As revised, $3.2 million of the additional costs recorded through December 31, 2004 are incremental Commission jurisdictional costs, and according to SDG&E, the balance of $1.5 million is non-incremental and should be excluded from the Wildfires Account.

Memo Account-Eligible Wildfire Costs
Including Update & Errata

| Memo Account-Eligible Wildfire Costs including Update & Errata |  |  |  |
| --- | --- | --- | --- |
|  | Total CPUC (a) | Memo Account (b) | Current Rates (b) |
| O&M Expense |  |  |  |
| Pre-Update O&M | $16,463 | $12,055 | $4,408 |
| Internal Labor | $10 | - | $10 |
| Materials | 5 | - | 5 |
| Overhead | 9 | 44 | (35) |
| Vehicle Charges | (2) | - | (2) |
| External Labor | 8 | - | 8 |
| Services/Other | 209 | (17) | 226 |
| Update & Errata | $239 | $27 | $212 |
| Total O&M | $16,702 | $12,082 | $4,620 |
| Capital Costs |  |  |  |
| Pre-Update Capital | $41,548 | $25,605 | $15,943 |
| Internal Labor | $47 | $5 | $42 |
| Materials | $19 | 19 | - |
| Overhead | $1,227 | 5 | 1,222 |
| Vehicle Charges | $30 | - | 30 |
| External Labor | $342 | 342 | - |
| Services/Other | $2,807 | 2,745 | 62 |
| Update & Errata | $4,472 | $3,116 | $1,356 |
| Total Capital | $46,020 | $28,721 | $17,299 |
| Total Wildfire | $62,722 | $40,803 | $21,919 |

On February 9, 2004, ORA and UCAN filed comments on SDG&E’s updated testimony and errata.  ORA had no objections.  UCAN was succinct: it questioned the late inclusion of $600,000 of costs incurred prior to May 31, 2004; and secondly, UCAN pointed out that the update and errata include $209,000 of environmental costs which it believes supports UCAN’s contention that the environmental costs are connected with the cost of installation of a capital project and should be capitalized.  UCAN does not convince us that SDG&E’s earlier omission is somehow unrecoverable when included in an update.  We know from SDG&E’s testimony and ORA’s review that SDG&E established reasonable accounting procedures to segregate and track the Wildfire costs.  Corrections and updates are not innately unreasonable.  We will not make this adjustment.  As already discussed, we did find that SDG&E’s practice under-capitalized environmental costs (and other overheads) and therefore we will direct SDG&E capitalize $176,000 of the late-filed environmental costs using the same 84.2% as required above.

# Comments on Proposed Decision

The proposed decision of the ALJ in this matter was mailed to the parties in accordance with Pub. Util. Code § 311(d) and Rule 77.1 of the Rules of Practice and Procedure.

On August 8, 2005 SDG&E and UCAN filed timely comments on the ALJ’s proposed decision and Commissioner Kennedy’s alternate.

SDG&E recommended adoption of Commissioner Kennedy’s alternate, with some corrections, and opposed the ALJ’s proposed decision in its entirety.  To the extent SDG&E’s comments reargued positions taken in briefs they were accorded no weight.  SDG&E did correctly identify the need to modify the amortization period, due to the delay in issuing this decision, and that change has been made.  Additionally, the intention of the ALJ’s proposed decision was to correctly reflect the final data including all exhibit errata and those changes have been made.  Finally, SDG&E proposed greater specificity for the ordering paragraphs to authorize and implement rate recovery and those changes have been made.

UCAN recommended adoption of the ALJ’s proposed decision and opposed Commissioner Kennedy’s alternate in its entirety.  UCAN proposed one correction to the ALJ’s proposed decision: to re-characterize ORA’s position as a settlement with SDG&E.  ORA and SDG&E did not settle within the meaning of Rule 51 and this change is not appropriate.  ORA’s participation and recommendations have been correctly included herein.

# Assignment of Proceeding

Susan P. Kennedy is the Assigned Commissioner and Douglas M. Long is the assigned Administrative Law Judge and principal hearing officer in this proceeding.

- Findings of Fact

- As a result of massive wildfires, on October 26, 2003, then-Governor Davis declared a state of emergency for San Diego County.  The following day, October 27, 2003, President Bush also declared a state of emergency for San Diego County.

- Approximately 3,200 power poles, 400 miles of wire, 400 transformers and more than 100 other pieces of related equipment were damaged by the fire and needed to be replaced by SDG&E.  In total, SDG&E spent $71.1 million to replace lost equipment and restore service.

- SDG&E’s actions were reasonable when it activated its Emergency Operations Center.  As a result of the damage, SDG&E decided it was necessary to call on other utilities for assistance to restore service.  The use of mutual assistance crews and additional contractor personnel was necessary to restore service in a timely fashion.  Senior management was involved in the oversight of the project and SDG&E systematically tried to reestablish service as quickly as possible.

- Based on the high cost of premiums and limits on coverage, SDG&E had no reasonable insurance option to offset the costs of the Wildfires.

- Resolution E-3238 established the Commission’s requirements for invoking and applying the CEMA tariff provisions.  SDG&E complied with these requirements by informing the Commission in a timely manner and establishing separate accounting and other controls for the Wildfires’ costs.  The company reasonably assumed that direct labor at straight -time (i.e., excluding overtime) was not includable in the Wildfire Account, but overtime labor and other costs incurred solely to restore service are incremental to existing costs already included in rates.

- ORA’s examination of SDG&E’s actions was focused on ensuring that only incremental costs were included in the Wildfire Account.  ORA found that SDG&E included in the Wildfire Account $9,416 for newspaper advertisements to thank the utilities that provided mutual assistance crews.  This cost was not necessary to restore service and is not reasonably included in the Wildfire Account.

- ORA did not review the reasonableness of expenditures for a cost causation perspective or from a cost reduction or avoidance perspective.

- UCAN applies an additional reasonableness test to SDG&E’s request that was not employed by ORA.  UCAN proposes that costs incurred by SDG&E should be compared to a fair market price for the commodity.

- SDG&E provided meals, beverages and snacks in large number to all workers, including, incidentally, some police, fire and other workers involved in fighting the Wildfires or SDG&E’s efforts to restore services.  SDG&E utilized established catering firms that it believed could provide adequate service in numerous locations throughout the affected service territory.

- SDG&E’s vendors charged for food service on the basis of the number of meals served, but the measurement was a standard assumption of the size of food portions that would constitute a meal.  Many workers often ate the caterer’s equivalent of multiple meals as a result of long hours and hard work.  No accurate head-count was maintained.  SDG&E did negotiate a generic 10% reduction to the bills from one major vendor after the Wildfires.

- UCAN compared certain food service costs to other viable measures of market prices and thus applied a reasonable comparison standard to the costs incurred by SDG&E.  SDG&E did not show that it made any analysis of the costs charged by vendors, and therefore it unreasonably relied on the vendor contracts to justify the reasonableness of the costs incurred.  UCAN showed that SDG&E’s vendors made excessive charges for drinks and snacks, including bottled water, Gatorade and Red Bull, exceeding the prices available to the vendors even at COSTCO, an accessible large retail/wholesale outlet, by $582,300.

- SDG&E did not exercise reasonable control over all vendor costs and ratepayers should not have to pay $582,300 in excess of market prices.

- The CEMA process as authorized in Resolution E-3238 allows SDG&E the opportunity to recover its reasonable costs incurred as a result of a catastrophic event.  Without this ratemaking exception, SDG&E would have no option but absorb all of its Wildfires expenses and would only recover capital expense changes to rate base in a subsequent rate setting proceeding such as the next general rate case.

- Seventy three percent of SDG&E’s destroyed poles (2,096) were over 15 years old, which put them on a 10-year inspection and treatment cycle.  No inspection will be needed on the new replacement poles during the next 10 years and this will avoid inspections at $34.29 per pole. Of those older destroyed poles, 30% were already inspected prior to the fire, so SDG&E avoided inspecting 1,235 destroyed poles at an estimated savings of $42,348.  It is equitable to offset this clear future savings of $0.042 million against the much larger cost of $37.600 million requested by SDG&E under the CEMA ratemaking exception.

- In order to allow for a full cost recovery, Commission ratemaking conventions allow SDG&E to increase its revenue requirement to collect from all customers the amount of revenue otherwise uncollectible from a few, plus the franchise fees it pays on the total revenue requirement.  SDG&E correctly calculated the gross-up factor as: 1 / 1 – (3.67% + 0.266%) = 1.041.

- The tree inventory maintained for vegetation management has increased since the Wildfires because damaged trees adjacent to the right-of-way are now monitored by SDG&E.  Many damaged trees in the right-of-way were not physically removed and remain in the inventory.

- The total cost of replacing long-lived assets destroyed by the Wildfires is higher because SDG&E expedited construction; this management decision resulted in incurring both higher costs, including overtime and mutual assistance, and additional costs, including meals and snacks, compared to slower methods of restoring service.  All of the costs are allocated between maintenance, which is a current expense, and capital expenditures, which reflect installing long-lived assets in rate base.

- SDG&E proposes to expense most of its support costs that are accounted for as overheads based on its interpretation of the applicable accounting standards that these costs were immediately “consumed” and should not be capitalized as a part of the costs of installing new long-lived assets in rate base.  SDG&E cannot identify any specific accounting rule supporting its interpretation.  Generally accepted accounting principles and ratemaking accounting authorized by the Commission require that all costs, including overhead and support services, associated with installing long-lived assets should be capitalized for recovery over their useful service life.

- UCAN recommends an allocation factor for support costs based on the allocation of labor costs to reflect the correct split of costs between expense and capital.  This method allocates 15.8% to current expense and 84.2% to capital expenditures.  UCAN’s proposal reasonably allocates support costs between expense and capital expenditures based on the labor devoted to current expense and long-lived assets.

- SDG&E incorrectly allocates nearly all environmental costs to expense without regard to the split between operating expense and capital expense of direct labor and materials.  UCAN’s proposal reasonably assumes that environmental costs should follow labor costs in the absence of any convincing justification by SDG&E to expense the costs currently.

- The appropriate allocation of support costs and environmental costs to capital expenditures still ensures that SDG&E has a reasonable opportunity to recover in rates its prudently incurred costs to restore service after the Wildfires.

- Rate recovery of the current expense portion of the Wildfire Account should occur over a reasonably short period of time unlike the capital expenditure portion that should be recovered over the useful service life of the new assets.  It will be less disruptive and more convenient to customers if the current expense portion is amortized over the 15-months from October 1, 2005 through December 31, 2006.  This also strikes a balance between the respective SDG&E and UCAN proposals of 12 and 24 months.

- SDG&E employees are eligible for incentive compensation under a performance evaluation plan where the actual incentive is based upon their performance in relationship to specific goals and objectives.  SDG&E accrued $726,000 for incentive compensation, and allocated $426,000 as incremental costs to be recovered in the Wildfire Account.  SDG&E did not demonstrate that employees were specifically awarded incentive compensation or that it was solely attributable to their performance during the Wildfires service restoration.

- Conclusions of Law

- The disaster declarations issued by the Governor and the President for the 2003 Wildfires constitute an event declared to be a disaster by competent state or federal authorities for purposes of § 454.9.

- Use of the Wildfire Account for recording and recovering the costs incurred by SDG&E to restore utility service to customers, repair, replace or restore damaged facilities, as caused by the 2003 Wildfires, is appropriate under the statute as written.

- SDG&E alone bears the burden of proof to show that its costs were reasonable and are eligible for recovery under the CEMA tariff.

- The Commission’s Standard for Prudent Managerial Action is the appropriate standard to apply to the costs recorded in the Wildfire Account.

- The Commission is not dependent on an intervenor performing any specific analysis before the Commission may determine the reasonableness of a pending matter.

- Rate recovery of various support costs can be reasonably allocated between expense and rate base in proportion to the allocation of direct labor.

ORDER

IT IS ORDERED that:

- The reasonable total recoverable costs resulting from this Catastrophic Event Memorandum Account (Wildfire Account) application is $39.752 million to be collected in retail rates charged by San Diego Gas & Electric Company (SDG&E).

- SDG&E’s electric department expense portion and the 2003-2005 capital-related revenue requirement portion shall be amortized in rates beginning October 1, 2005 and ending December 31, 2006.  The 2006-2007 capital-related revenue requirement shall be recovered as an annual adjustment to base margin rates effective January 1 of 2006 and 2007.

- SDG&E's gas department Wildfire costs shall be recovered by transferring the gas department Wildfire Account balance to the Core and to the Noncore Fixed Cost Accounts.  SDG&E shall file an advice letter to allocate the gas department's Wildfire costs between Core and Noncore.  The Wildfire costs allocated to the Core and Noncore Fixed Costs Accounts shall be recovered in rates as a part of the ongoing operation of these accounts. The advice letter will be effective on the date filed subject to Energy Division determining that the filings are in compliance with this order.

- SDG&E shall file a compliance advice letter with the Commission’s Energy Division no later than 5 days prior to the effective date of the October 1, 2005 amortization described in Ordering Paragraph No. 2.  SDG&E shall serve the advice letter on the service list for this proceeding.  The advice letter shall include the calculations of the rate amortization to recover the current portion of the Wildfire Account and include a description of the recovery in the Preliminary Statement.  The advice letter will be effective on the date filed subject to Energy Division determining that the filings are in compliance with this order.

- SDG&E shall include the 2006 and 2007 capital-related revenue requirement in the advice letters filed to implement the authorized changes to 2006 and 2007 base margin rates as authorized in D.05-03-023.

- Application 04-06-035 is closed.

This order is effective today.

Dated _____________________, at San Francisco, California.

APPENDIX A

Lists of Appearances

DAVID A. EBERSHOFF

Attorney at Law

FULBRIGHT & JAWORSKI, L.L.P.

865 S. Figueroa St. Ste. 2900

Los Angeles,  CA 90017

(213) 892-9327

Fax # (213) 680-4518

Appearing for Apple Valley Water Company

Applicant

debershoff@fulbright.com

EDWARD N. JACKSON

PARK WATER COMPANY

9750 Washburn Rd.

Downey,  CA  90241-7002

(562) 861-5902

Appearing for Apple Valley Ranchos Water Company

Applicant

ed@parkwater.com

JASON REIGER

Attorney at Law

CALIFORNIA PUBLIC UTILITIES COMMISSION

505 Van Ness Ave.

San Francisco,  CA  94102

(415) 703-2262

Appearing for ORA

Intervenor

jzr@cpuc.ca.gov

STATE SERVICE

YOKE W. CHAN

Office of Ratepayer Advocates

505 Van Ness Ave.

San Francisco,  CA  94102

(415) 703-1909

Appearing for ORA

(End of APPENDIX A)

Application, pp. 1-2.

As quoted in the Application, from “California Fire Siege 2003 – The Story:  October 21 – November 4, 2003” (Preface).

As quoted in the Application, Id. (Introduction).

Ex. SDG&E-1, Testimony of Steven D. Davis and in more detail in Ex. SDG&E-2, Testimony of Scott P. Furgerson.

CPUC Resolution E-3238, dated July 24, 1991.

Application, p. 3.

There are some slight rounding differences in the two exhibits that are not material here.  In the adopted recovery we identify the accurate reasonable jurisdictional allocation.

Administrative Law Judge’s Ruling Requiring San Diego Gas & Electric Company to Provide Further Information to Supplement its Application.  The Ruling identified 6 specific deficiencies and directed SDG&E to provide adequate documentation or further explanations, as appropriate, in the form of additional testimony.

Administrative Law Judge’s Second Ruling Requiring San Diego Gas & Electric Company to Provide Further Information to Supplement its Application.

Scoping Memo, pp. 3-4.

This advantage is discussed at length in D.00-02-046, a recent rate case for PG&E.

D.87-12-067, 27 CPUC 2d, 1, 21, and footnote 1 at p. 169.

UCAN Opening Brief, p. 9, citing D.01-10-031 Ordering Paragraph 26.

Decision 02-08-064 (2002 Cal. PUC LEXIS 534; 219 P.U.R.4th 421).

D.88-03-036 (1988 Cal. PUC LEXIS 155,*7; 27 CPUC2d 525).

D.87-06-021 (1987 Cal. PUC LEXIS 588, *28-29, 24 CPUC 2d 476).

D.89-02-074 (1989 Cal. PUC LEXIS 128, *11, 31 CPUC 2d, 236).

D.90-09-088 (1990 Cal. PUC LEXIS, 847, *23-25, 37 CPUC 2d 488, 499), based on language in D.87-06-021, and quoted with approval in D.98-09-040 (1998 Cal. PUC LEXIS 972 *34-35).

Ibid.

- D.01-02-075, Conclusion of Law No. 1: “The burden of proving that the settlement is fair is on the proponents.”

Ex. SDG&E-1, pp. 2-3.

Ex. SDG&E-3, p. 15.

Ex. ORA-1, pp. 2-4, 3-3, 4-3, 6-3, 7-2, and 8-2.

Ex. ORA-1, pp. 1-4 and 1-5.

Transcript, pp. 155-183. UCAN questioned ORA’s witness on the criterion used by ORA in its testimony to derive its opinion that the costs were reasonable.

Ex. ORA-1, p. 7-2.

See, for example, Transcript pp. 128-129.

Ex. ORA-1, p. 7-2.

D.01-02-075, p. 11.

This would equate to the “cost reduction” standard included in D.01-02-075.

Ex. UCAN-151, pp. 2-3, compared to data in Ex. SDG&E-2, p. 30.

Ex. UCAN-151, p.3, citing to UCAN Data Request (DR) 3, Question (Q) 12, and DR 1, Q 2.

UCAN adds 7.75% for sales tax and then deducts a 10% discount from the total.  UCAN initially calculated an adjustment of $738,400, corrected at hearing by the witness.

UCAN does not say SDG&E should have done “snack-runs” to COSTCO, only that SDG&E was charged too much by the vendors it used for food services.

Ex. SDG&E-4, pp. 2-3.

Ex. SDG&E-4, p. 8.

Transcript, p. 29.

UCAN Opening Brief, p. 7, and shown in detail in footnotes 63 and 64 on p. 23.

Ex. UCAN-151, p. 6, see also UCAN DR 3, Q 15, and DR 3, Q 18.

Ex. UCAN-151, pp. 6-7.  (1,235 poles @ $34.29 = $42,348.)

Ex. SDG&E-5 p. 2.  (Rebuttal.)

Ex. SDG&E-5, p. 2.

Ex. SDG&E-3, attached Exhibit D-4.  (SDG&E captioned attachments to testimony as “exhibits,” thus Ex. 3 contains attachments also titled as exhibits.)

Ex. SDG&E-5, p. 6.

Transcript, p. 115, deleting Section B. Franchise Fees and Uncollectibles, in Ex. UCAN-1 at p. 10.

Ex. UCAN-151, pp. 8-9, relied on Ex. 4, Exhibit G-9, G-12 and H-13 for the support costs, and Ex. SDG&E-3, Exhibit D-1 for the labor costs to calculate the split.

Ex. SDG&E-4, p. CAS-3, lines 10-18.

Transcript, pp. 112-113.

Ex. SDG&E-1, pp. 9-11 citing numerous public accolades.

Ex. UCAN-1, p. 9.

Ex. SDG&E-4, attached Exhibit J, pp. 1 through 3.  Incremental environmental costs as included by SDG&E in the Wildfires Account.

SDG&E noted in the evidentiary hearing that in another proceeding there is a proposal to substantially increase SDG&E’s allocation of costs for energy contracts held by the Department of Water Resources.

See D.04-12-015, p. 10 orders an application for test year 2004.  Phase 2 is pending on A.02-12-028 addressing post-test year 2004 ratemaking.  Annual adjustments have been consistently allowed in the past.

Ex. ORA-1, p. 3-4, and Transcript, pp. 130-131.

Ex. SDG&E-4, attached Exhibit J, p. 3.

Transcript, p. 192.

A.02-12-028, Ex. 34, p. GJR-5 and GJR-6, Transcript in A.02-12-028, pp. 1416 ff., cross examination of Joyce Rowland.  We may consider this information under the Commission’s Rule 72 and as a Party Admission.

Transcript, p. 109.

Transcript, p. 111.

Filed on January 18, 2005.

“Circuit 79 is a 12 kV electric distribution line that traverses through Cuyamaca Rancho State Park.  Circuit 79 was extensively damaged during the firestorm and as a result had to be rebuilt and relocated.”  (Ex. SDG&E-9. p. 1-2.)

Ex. SDG&E-9. p. 1.

Ex. SDG&E-10, p 2.

“Circuit 79 is a 12 kV electric distribution line that traverses through Cuyamaca Rancho State Park.  Circuit 79 was extensively damaged during the firestorm and as a result had to be rebuilt and relocated.”  (Ex. SDG&E-9. p. 1-2.)

UCAN comments, p. 3.