## 818PEPDraft
Activity | Description | Audience | Shared or Individual Service Provider Effort | Start Date | Completed Date
1 | Effective date of decision approving 818 area code overlay | NA | NA |  | Decision date (DOD)
2 | NANPA 818 implementation meeting | CPUC Staff and Industry | Shared |  | 2nd Tuesday after DOD
3 | Email to industry asking for participation on task force & subcommittees | Industry | Shared |  | 3 weeks after DOD
4 | Overlay information distributed internally as job aid for customer service representatives to answer customer questions. Representatives should not need to refer questions to the CPUC. | Customer service representatives | Individual |  | 1 month after DOD
5 | 818 overlay update to industry websites | All customers | Individual |  | 4 months after DOD
6 | News release describing 818 area code relief plan for distribution within the 818 area code including chambers of commerce and local governments | All customers | Shared |  | 4 months after DOD
7 | Notify California Relay Services to send messages alerting customers to 1 + 10 digit dialing requirement in 818/747 area codes | Hearing impaired customers | Shared |  | 5 months after DOD
8 | Customer Notification No. 1: Announce the new area code plan. Include information about 1 + 10-digit dialing and indicate affected areas | All customers | Individual |  | 5 months after DOD
9 | Provid letters with the information in Customer Notification No. 1, as well as PEP Task Force contact ifnormation and an offer to provide industry speakers, to senior, consumer and other advocacy/activist organizations, chambers of commerce, city councils and other key government agencies, Burbank airport, alarm service providers and public safety organizations throught the 818 area code. | Senior, consumer and other advocacy/activist organizations, chambers of commerce, city councils and other key government agencies, Burbank airport, alarm service providers and public safety organizations | Shared |  | 5 months after DOD
10 | Begin Permissive Dialing |  |  | 6 months after DOD on Saturday | 12 months after DOD
11 | Provide targeted information to schools by letter, sticker and worksheet. Timing may be modified to accommodate the school year. | Schools | Shared | 5 months after DOD | 7 months after DOD
12 | Published Directories: Add information on cover to alert customers in 818 area code | All customers | Individual |  | 9 months after DOD
13 | Offer industry appearances on local radio and TV talk shows | All customers | Shared | 3 1/2 months after DOD | 9 months after DOD
14 | Correct payphone signage to include updated dialing instructions | All customers | Individual |  | 11 months after DOD
15 | News releases to media serving 818 area code and adjacent area codes and statewide regarding start of mandatory dialing | Statewide | Shared |  | 11 months after DOD
16 | Disseminate information in relevant zoned editions of major newspapers, ethnic media, radio and television through paid advertising. (Note: The bulk of the information should be disseminated in the three weeks preceeding the beginning of mandatory 1+10 digit dialing.) | All customers | Shared | 9 months after DOD | 11 months after DOD
17 | Offer industry appearances on local radio or TV talk shows | All customers | Shared | 9 months after DOD | 11 months after DOD
18 | Customer Notification #2. Announce the new area code plan. Include information about mandatory 1 + 10 digit dialing and indicate affected areas. | All customers | Individual |  | 11 months after DOD
19 | Provide letters with the information in Customer Notification No. 2, as well as PEP Task Force contact ifnormation and an offer to provide industry speakers, to senior, consumer and other advocacy/activist organizations, chambers of commerce, city councils and other key government agencies, Burbank airport, alarm service providers and public safety organizations throught the 818 area code. | Senior, consumer and other advocacy/activist organizations, chambers of commerce, city councils and other key government agencies, Burbank airport, alarm service providers and public safety organizations | Shared |  | 11 months after DOD
20 | Complete implementation of recorded message announcing mandatory dialing | All customers | Individual |  | 11 months after DOD
21 | Conduct a balanced and statistically significant survey of customers in 818 area code, including elderly, disabled and non-English speakers, to determine level of awareness of overlay and dialing change and submit the results to the Director of the Telecommunications Division. The proposed survey methodology shall be submitted to the Director of the Telecommunications Division for approval prior to implementation. | All customers including the elderly, disabled, non-English speakers | Shared |  | 11 months after DOD
22 | Begin Mandatory Dialing |  |  | 12 months after DOD on Saturday
23 | 747 numbers assigned and implementation completed |  |  | 13 months after DOD, 1 month after mandatory dialing