A.01-03-036  MLC/k47


MLC/k47  8/29/2001

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF CALIFORNIA

	In the Matter of the Application of San Diego Gas & Electric Company (U 902-E) for a Certificate Of Public Convenience & Necessity Valley-Rainbow 500kV Inter-Connect Project.


	Application 01-03-036

(Filed March 23, 2001)




ADMINISTRATIVE LAW JUDGE’S RULING
MODIFYING SCHEDULE

On August 13, 2001, Commissioner Duque issued an Assigned Commissioner’s Ruling establishing the schedule and scope of the Valley-Rainbow proceeding.  On August 16, 2001, counsel for San Diego Gas & Electric Company (SDG&E) and the Office of Ratepayer Advocates (ORA) contacted me to discuss the possibility of modifying the adopted schedule.  At my request, SDG&E initiated a conference call amongst the parties in order to develop a recommended schedule.  SDG&E, the California Independent System Operator (ISO), Southern California Edison Company (SCE), ORA, Save Southwest Riverside County, California Alliance for Utility Safety and Education, Utility Consumers Action Network, the City of Temecula and the Domenigonis participated in the call.

On August 17, 2001, counsel for SDG&E forwarded a revised schedule to me indicating that it represented a consensus of the parties participating in the call.  After consulting with Commissioner Duque’s office, we will modify the schedule as set forth below.  The revised schedule will be adhered to as closely as possible.

	Event
	Date

	Application Filed
	March 23, 2001

	Application Deemed Complete
	April 23, 2001

	Prehearing Conference
	June 21, 2001

	Notice of Preparation Issued
	June 25, 2001

	CEQA Scoping Meetings
	July 10 - 12, 2001

	Assigned Commissioner Scoping Memo Issued
	August 13, 2001



	Revised Schedule Issued
	August 27, 2001

	Event
	Need Issues
	All Other Issues

	SDG&E Testimony served
	October 5, 2001
	May 9, 2002

	ISO Testimony served
	October 5, 2001
	May 30, 2002

	ORA Testimony served
	December 17, 2001
	May 30, 2002

	Intervenor Testimony served
	January 30, 2002
	May 30, 2002

	Rebuttal Testimony served
	February 25, 2002
	June 20, 2002

	Case Management Statement Due
	March 4, 2002
	June 26, 2002

	Prehearing Conference
	March 6, 2002
	July 1, 2002

	Evidentiary Hearings Begin
	March 11-22, 2002
	July 8-26, 2002

	Concurrent Opening Briefs Filed/ Request for Final Oral Argument
	April 19, 2002
	August 23, 2002

	Concurrent Reply Briefs Filed
	May 10, 2002
	September 13, 2002

	Closing Argument before Assigned Commissioner
	May 16, 2002
	September 20, 2002

	Event
	Date

	Draft EIR expected
	February 2002

	ALJ and parties tour project route and alternatives 
	April/May 2002

	Public Participation Hearings
	April/May 2002

	Final EIR published
	July 2002

	Draft Decision Certifying Final EIR issued
	August 2002

	Final Decision Certifying EIR

	September 2002

	Proposed Decision on CPCN
	December 2002

	Final Commission Decision
	January 2003


The Assigned Commissioner’s Ruling established certain other filing dates for additional information.  Counsel for SDG&E represents that SDG&E and the ISO will file and serve the requested material by the September 5, 2001 filing date established in the Assigned Commissioner’s Ruling. SCE may file and serve its requested materials by October 5, 2001 as requested via counsel for SDG&E.

Therefore, IT IS RULED that the schedule of this proceeding is as set forth above in this ruling.

Dated August 29, 2001, at San Francisco, California.

	
	
	/s/  MICHELLE COOKE

	
	
	Michelle Cooke

Administrative Law Judge


CERTIFICATE OF SERVICE

I certify that I have by mail this day served a true copy of the original attached Administrative Law Judge’s Ruling Modifying Schedule on all parties of record in this proceeding or their attorneys of record, or if so requested, by electronic means.

Dated August 29, 2001, at San Francisco, California.

	/s/  KRIS KELLER

	Kris Keller


NOTICE

Parties should notify the Process Office, Public Utilities Commission, 505 Van Ness Avenue, Room 2000, San Francisco, CA  94102, of any change of address to insure that they continue to receive documents. You must indicate the proceeding number on the service list on which your name appears.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * 

The Commission’s policy is to schedule hearings (meetings, workshops, etc.) in locations that are accessible to people with disabilities. To verify that a particular location is accessible, call: Calendar Clerk (415) 703-1203.

If specialized accommodations for the disabled are needed, e.g., sign language interpreters, those making the arrangements must call the Public Advisor at (415) 703‑2074, TTY 1-866-836-7825 or (415) 703-5282 at least three working days in advance of the event.

�  Rule 77.7(f)(8) provides that the Commission can waive or reduce the period for public review and comment “for a decision under a federal or California Statute (such as the California Environmental Quality Act or the Administrative Procedure Act) that both makes comprehensive provision for public review and comment and sets a deadline from initiation of the proceeding within which the Commission must resolve the proceeding.”  





105234
- 1 -
- 3 -

